## Q2 16-17
The Dudley Group NHS Foundation Trust Performance in Initiation Quarter 2 2016/17
Id | Research Ethics Committee Ref Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Per-mission | Duration between NHS Per-mission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed by Sponsor | Date Site Confirmed | Non confirmation status | Date site ready to start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
86561 | 16/EM/0193 | 190690 | HRA Approval | The dal-GenE trial: A phase III, double-blind, randomised placebo-controlled study to evaluate the effects of dalcetrapib on cardiovascular (CV) risk in a genetically defined population with a recent Acute Coronary Syndrome (ACS) |  |  | Yes | 2016-09-19 |  |  |  | No | 2016-02-02 | 2016-06-17 | 2016-06-14 | 2016-07-13 | 2016-07-12 | Sponsor declined confirmation | 2016-09-18 | Y |  |  | Y | Y | [5 empty] | Sponsor requirement that US forms must be completed for all staff prior to greenlight. | Both
86565 | 14/WA/1056 | 154468 | NHS Permission | AML 19: Adults with Acute Myeloid Leukaemia or High-Risk Myelodysplastic Syndrome (AML19) | 2016-01-04 | 2016-01-05 | Yes | 07/012016 | 1 | 2 | 3 | Yes
86566 | 14/YH/1259 | 163195 | NHS Permission | ALPHA: Comparison of Alitretinoin with PUVA as the first line treatment in patients with severe chronic hand eczema | 2015-11-02 | 2015-11-06 | No |  | 4 |  |  | No | [11 empty] | E | [5 empty] | Phototherapy was supposed to be carried out by clinical team, but subsequent staffing issues made this impossible. Research team trained in phototherapy in Oct 2016 in order to initiate study. | NHS Provider
89733 | 15/SC/0443 | 173722 | NHS Permission | OPTIMISE: CAIN457A3302 Long term clear skin maintenance treatment optimization in patients with moderate to severe chronic plaque psoriasis: A randomized, multicenter, open-label with blinded-assessment, comparative, 52 week study to evaluate the efficacy, safety andtolerability of secukinumab 300 mg s.c. | 2015-10-20 | 2015-10-23 | Yes | 2015-12-03 | 3 | 41 | 44 | Yes
89736 | 15/YH/0428 | 188418 | NHS Permission | DUAL VIII: A 104-week, multi-centre, multinational, open-label, two-arm parallel, randomised to insulin degludec/liraglutide (IDegLira) vs.insulin glargine therapy in subjects with T2DM inadequately controlled on OAD(s) | 2015-11-30 | 2015-12-03 | Yes | 2016-02-24 | 3 | 83 | 86 | No | [16 empty] | Y | Pharmacy required further clarification from Sponsor for safe dispensing | Both
89737 | 12/EE/0445 | 106714 | NHS Permission | PREVENTT: (Preoperative intravenous iron to treat anaemia in major surgery) | 2016-03-01 | 2016-03-02 | Yes | 2016-09-15 | 1 | 197 | 198 | No | [12 empty] | Y | Y |  |  |  | 1. complex blinding procedure to sort out; 2. using a totally new clinical pathway; 3. possibly overestimation of levels of anaemia in Gynae patients requiring new lines of communication | NHS Provider
89744 | 15/NS/0070 | 183762 | HRA Approval | BASIL 3: Multi-centre randomised controlled trial of clinical and cost-effectiveness of drug coated balloons, drug eluting stents and plain balloon angioplasty with bail-out bare metal stent revascularisation strategies for severe limb ischaemia due to atherosclerotic femoro-popliteal, with or without infra-popliteal involvement, peripheral arterial disease |  |  | Yes | 2016-09-07 |  |  |  | No | 2016-04-26 | 2016-08-01 | 2016-04-27 | 2016-08-23 | 2016-08-23 | [13 empty] | Neither
89780 | 14/SC/0171 | 120104 | NHS Permission | ADD ASPIRIN: A phase III, double blind, placebo controlled, randomised trial assessing the effects of aspirin on disease recurrence and survival after primary therapy in common non-metastatic solid tumours | 2016-03-29 | 2016-04-08 | Yes | 2016-05-26 | 10 | 48 | 58 | Yes | [11 empty] | Y |  | Y |  |  |  | Staffing levels in April and May prevented research nurses actively seeking out potential participants. Staffing levels subsequently improved in June 2016 | NHS Provider
89791 | 15/NW/0698 | 183781 | NHS Permission | REGAIN: (LPS14060) A randomized, open-label, 2-arm parallel group real world pragmatic trial to assess the clinical and health outcomes benefit of transition to Toujeor in basal insulin treated patients with uncontrolled type 2 diabetes mellitus | 2016-03-29 | 2016-04-21 | Yes | 2016-09-23 | 23 | 155 | 178 | No | [13 empty] | Y | Y |  |  | Pharmacy required further time and clarification from Sponsor for safe dispensing | NHS Provider
89794 | 15/NW/0697 | 183760 | NHS Permission | REACH (LPS13931) A twenty-six week, randomized, open-label, 2-arm parallel group real world pragmatic trial to assess the clinical and health outcomes benefit of Toujeo® compared to standard of care insulin for initiating basal insulin in insulin naive patients with uncontrolled type 2 diabetes mellitus, with 6-month extension | 2016-03-29 | 2016-04-21 | Yes | 2016-08-25 | 23 | 126 | 149 | No | [13 empty] | Y | Y |  |  | Pharmacy required further time and clarification from Sponsor for safe dispensing | NHS Provider